## Sheet1
GANTT CHART TEMPLATE					Smartsheet Tip ➜					A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.

PROJECT TITLE: memories application					INSTUTUTE & DEPARTMENT NAME					AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
PROJECT GUIDE Prof.Manjusha Kashilkar					DATE					10/14/22

WBS NUMBER	TASK TITLE	TASK OWNER	START DATE	DUE DATE	DURATION(Weeks)	PERCENTAGE OF TASK COMPLETE	PHASE ONE					PHASE TWO
				WEEK 1					WEEK 2					WEEK 3					WEEK 4					WEEK 5					WEEK 6					WEEK 7					WEEK 8					WEEK 9					WEEK 10					WEEK 11					WEEK 12					WEEK 13					WEEK 14
				M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F
1	Project Conception and Initiation
1.1	Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project	Hitesh Sachdev / Siddhesh Sawan / Aman Yadav	7/11/22	7/22/22	2	100%
1.2	Identifying the functionalities of the Mini Project	Hitesh Sachdev / Siddhesh Sawan / Aman Yadav	7/25/22	8/5/22	2	100%
1.3	Discussing the project topic with the help of paper prototype.	Hitesh Sachdev / Siddhesh Sawan / Aman Yadav	8/8/22	8/19/22	2	100%
1.4	Designing the Graphical User Interface(GUI)	Hitesh Sachdev / Siddhesh Sawan / Aman Yadav	8/22/22	9/9/22	3	100%
1.5	Presentation I	Hitesh Sachdev / Siddhesh Sawan / Aman Yadav	9/12/22	9/16/22	1	100%
2	Project Design and Implementation
2.1	Detail website Design	Hitesh Sachdev / Siddhesh Sawan / Aman Yadav	9/19/22	9/23/22	1	100%
2.2	Integration of all Webpages	Hitesh Sachdev / Siddhesh Sawan / Aman Yadav	9/26/22	9/30/22	1	100%
2.3	Report Writing	Hitesh Sachdev / Siddhesh Sawan / Aman Yadav	10/3/22	10/7/22	1	100%
2.4	Presentation II	Hitesh Sachdev / Siddhesh Sawan / Aman Yadav	10/10/22	10/14/22	2	100%